## Sheet1
Risk Register for UOW revamp room booking system
Date: 11 Oct 2022
Project Name: | Revamping of University of Wollongong room booking system
ID No. | Rank | Risk | Category | Potential Responses | Risk Owner | Probability | Impact | Residual Risk
1 | 1 | Members are new and not used to working with each other, not understanding each other’s working styles. | HR | Organise Team Bonding | Theophilus | H | M | Some team members may still find it hard to get along and work openly after the Team Bonding events.
2 | 2 | Members are unclear of their roles in the project | HR | Give members the opportunity to clarify regarding their roles and responsibilities. Create a clear and concise Team Charter to alleviate the risk. | Theophilus | M | H | Members might still not fully understand the full list of their responsibilities in the project.
Risk Register for UOW revamp room booking system
Date: 17 Oct 2022
Project Name: | Revamping of University of Wollongong room booking system
ID No. | Rank | Risk | Category | Potential Responses | Risk Owner | Probability | Impact | Residual Risk
1 | 1 | Team members unsure of organisational hierarchy chart thus unsure of who to report or work with. | HR | Referring back to the HR plan and organisation chart. | Theophilus | M | L | NIL
Risk Register for UOW revamp room booking system
Date: 25 Oct 2022
Project Name: | Revamping of University of Wollongong room booking system
ID No. | Rank | Risk | Category | Potential Responses | Risk Owner | Probability | Impact | Residual Risk
1 | 1 | Not comprehending the changes across the project that might arise from the change request. | technical skills | Appoint Debra to be in charge of taking a deep and comprehensive look into the impact of the change request. | Debra | H | H | Might actually have a bigger impact to our project timeline than we expected
2 | 2 | Not enough Budget adjustments based on the new change request | financial | Filled up the change request form accordingly and requested for the extra amount needed due to the new changes | Tsun Hong | M | H | Overlooking the amount of extra budget needed
3 | 3 | On-going programming will be affected by changes in project scope and schedule. | organisational | Try to reduce the effects the change request have on the ongoing programming by quickly establishing the changes in scope and schedule from the change request. | Debra | M | H | The schedule allocated for the Development Stage might still be affected.
Risk Register for UOW revamp room booking system
Date: 31 Oct 2022
Project Name: | Revamping of University of Wollongong room booking system
ID No. | Rank | Risk | Category | Potential Responses | Risk Owner | Probability | Impact | Residual Risk
1 | 1 | Not comprehending the changes across the project that might arise from the change request. | technical skills | Everyone will take time to go through all the changes completed for the change request to make sure that nothing is missed out. | Debra | L | H | NIL
Risk Register for UOW revamp room booking system
Date: 9 Nov 2022
Project Name: | Revamping of University of Wollongong room booking system
ID No. | Rank | Risk | Category | Potential Responses | Risk Owner | Probability | Impact | Residual Risk
1 | 1 | Test cases do not reflect real usage of the webpage. | Technical skills | Let everyone in the group to have a go at utilising the webpage, creating test cases that will adequately cover all cases of usage. | Bin Hui | H | H | Missing out on test cases thus failing to test the webpage comprehensively.
2 | 2 | Creating of room booking tutorial video, had to be simple so that it can be easily comprehended by the CIO, was also unsure if it will be better to include the audio or not | Technical skills | Watching a few explainer videos on youtube to understand how they make the video and get inspired from it and do a similar approach | Dominic | H | M | Still not being able to fully make an explainer video that can be understood easily